# Case Study:   Policy Recommendations for the Interface Between Customer Equipment and the Utility Advanced Metering Infrastructure to Facilitate Demand Response

# Diane S. Pepetone, L’Monte Information Services, Inc.

# Client: State Energy Commission

# Client’s Goals

1.  Understand regulatory implications of use cases being developed by a consortium of utilities and vendors for use in specifying the Advanced Metering Infrastructure (AMI) systems, including the interface with home area networks (HAN) and home automation systems.

2. Develop policy recommendations for the AMI-HAN interface that would protect privacy of customers and facilitate their effective participation in Demand Response programs.

My Responsibilities:

1. Identify project plan for accomplishing the client’s goals, and manage the project.

2. Produce regulatory use cases and policy recommendations for the AMI-HAN interface.

What Happened:

Based on initial reviews of use cases developed by the utilities, the client felt there were assumptions that might limit customer choice and privacy in the AMI-HAN interface, and limit vendor choice of communication technologies used in their systems.

After setting up a small task force of client and consultant subject matter experts, we met and chartered the project by defining the project scope and project metrics in the form of critical success factors and critical risks and issues.  From this input we laid out a plan of action, which started with an analysis of the utility use cases to understand what they proposed and to identify specific problems.

I developed Venn diagrams to represent how the utility use cases would affect all the key players.  The interaction between the spheres of the customer, the vendor and the utility made it clear that there were areas of overlap that implied a level of control by the utilities that was of concern.    Using this as a jumping off point, we developed regulatory use case scenarios that represented what the commission would like to see in terms of options for customers and vendors as well as utilities.

From the regulatory use case scenarios I developed rights-obligation activity models because they made explicit what rights and obligations were implied in our use case scenarios.   After several rounds of reviewing rights-obligation models, making changes to the regulatory use cases and deriving the new rights-obligation models, we had a set of regulatory use cases and rights and obligations that could be used in policy recommendations.

Project Outcome:

This project introduced the client to the use of requirements engineering for defining policy.  Using the Venn diagrams proved very powerful in representing overlaps of authority and control between the utility, the customer and the vendor.  The use case scenarios allowed the task force to work out what options they felt should be offered in the AMI-HAN interface, and the rights and obligation modeling showed them how those options would affect each of the key players.

Although not in the original project plan, the client decided that results warranted preparing a research report, which I prepared and presented to state energy commissioners, state public utility commissioners, representatives of the major utilities and other key stakeholders.